## Initial Plan
TASK | WEEK 1 | WEEK 2 | WEEK 3
Requirements Gathering
Design
Implementation
Data
ITEM DETAILS
LIST OF ITEMS
GUI
DISPLAY
MENU
VIEW
SEARCH
ADD
DELETE
UPDATE
Integration of functionalities
Testing

## Schedule Followed
Dates | Prasana | Sanjana | Shruti | Vindhya
2020-02-09 | Worked on understanding the business requirements
2020-02-10 | Planned the timeline of the project
2020-02-11 | Worked on the design of the system and responsibilities of each member
2020-02-12
2020-02-13 | Researched on Java GUI |  | Planned of using ArrayList for the Inventory Management
2020-02-14
2020-02-15 | Research and self-study
2020-02-16
2020-02-17 | Created GUI file usingJavaFrames | Created ProdDetail | Created ProductDetailsUsingList.java | Created View.java using JavaFrames
2020-02-18 | Created Second.java and Search.java using JavaFrames | Created Add and delete backend code |  | Created Delete.java using JavaFrames
2020-02-19 | Created Search and List for Backend |  | Created Add.java using JavaFrames | Created backend code for update.
2020-02-20 |  | Created Update.java using JavaFrames | Created backend for View and Search.
2020-02-21 | Discussed the issues while implementing the functionalites and started working on Integration
2020-02-22
2020-02-23 | Research and self-study
2020-02-24
2020-02-25 | Integration
2020-02-26 | Unit Testing
2020-02-27
2020-02-28 | Formatting and documentation